| Area for Development | Success Criteria | Evaluation |
| --- | --- | --- |
| - Impact Reduction (Catch up) -Our Three Tier Approach - Teaching - Targeted Academic support - Wider Strategies (Impact Reduction- reducing the impact in our children’s long-term understanding caused by Lockdown.) | Evidence shows A large proportion of children are settled Teachers have identified children needing interventions Interventions are effective. | HT reports to FGB. School Support discussions DCC, NLE, MAST. |

Tier 3 – Wider Strategies

Extensive outdoor leaning provision-Adventure Days, White Hall (AP1)

Christmas activities-singing.

Sport and Music tuition

Improve access to blended or home learning.

Ensure vulnerable pupils are supported with access to Teams and other technologies.

Identify other barriers (no tech) to learning at home for vulnerable families and engage with solutions.

Personal Growth. Continued (and adapted) use of Stars

Tier 2 – Targeted academic support

Catch Up®

2x English and 2x Maths

More TAs trained.

Teacher intervention- Weekly and same day

Targeted learning packs for EHCP/GRIP.  Development of recorded and live sessions.

Pre- teaching by TAs- teacher led

Parent/teacher meetings

Mentoring/Positive Play

Phonics- assessment and intervention programme.

Tier 1 – Teaching

Quality First Teaching.  Supported by CPD  Our main strategy

Implementation of Maths No Problem, supported by quality CPD (AP 4)

A broad and engaging curriculum that focus on knowledge and vocabulary acquisition. (AP7)

Talk 4 Writing strengthened and improved, supported by (AP 5)

Improved use of technology to facilitate home learning and intra-class learning.

Frequent low stake testing got ensure all students experience success.

Deliberately reduce work load to aid staff well-being and enable high quality responsive teaching.

Whole school implementation of EEF Metacognition Guidance.

| Action |  | Persons Responsible | Target date /completed by | Monitored by, method of monitoring | Evaluation of the impact | Resources/ Finance/Inset Catch up funding (CUF) |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Research to ensure effective use of catch up funding | HT (LA) | Nov 20 | HT report | FGB minutes | Ht time, LA consultaion |
|  | Tier 1 |  |  |  |  |  |
| 3.1.1 | Respond to questionnaire by improving online teaching and learning in case of bubble closure. (Move to Teams?) | SEO RC | Oct 20 | HT report | FGB minutes | Staff time |
| 3.1.2 | Develop Blended Leaning policy | SEO | Oct 20 | Policy at CSCLC | FGB minutes | HT time |
| 3.1.3 | Teachers to observe children in lessons | All teachers | ongoing | HT report | FGB minutes | Class time |
| 3.1.4 | Teachers to administer short pre-assessments in English and maths | All teachers | Dec 20 | HT report | FGB minutes | Class time |
| 3.1.5 | Teachers to identify children who have gaps in skills | All teachers | Oct 20 | HT report | FGB minutes | Staff time |
| 3.1.6 | End of term teacher assessment made and recorded | All teacher | Jan 6th | HT report | FGB minutes | Staff time |
| 3.1.7 | Pupil Progress meetings with teachers | HT All teachers | 10.12 20 4.12.20 Feb,,April, June | HT report | FGB minutes | Staff time |
| 3.1.8 | Agree the most important learning for each year group to give each child the best chance to continue their education journey. Reading, writing and maths. | All teachers | Sept 20 | HT report | FGB Minutes | Staff time |
| 3.1.9 | Plan teaching and interventions to address above (identified areas) | All teachers Catch Up® TAs | Oct 20 | HT report | FGB Minutes | Staff time |
| 3.1.10 | Ensure timetable is both structured to ensure time for extra key skills and flexible to allow teachers to respond to individual need. Keep under review. | HT | Oct 20 Dec 20 Feb 20 | HT report | FGB Minutes | Staff time |
| 3.1.11 | Metacognition Share materials | SEO | Dec 20 | HT report | FGB Minutes | Staff time |
| 3.1.12 | Meet to discuss. Teams meeting 6th Jan 4pm | All staff (inc TAs) | Jan 21 | HT report | FGB Minutes | Staff time |
| 3.1.13 | Implement | All staff | Jan 21 | HT report | FGB Minutes | Staff time |
| 3.1.14 | Monitor and evaluate | HT | March 21 | HT report | FGB Minutes | Staff time |
| 3.1.15 | Workload reduction. Use online IEP writers Train TA to support My Plan and iTrack data collection Use TAs to reduce teacher workload | HT | Nov 20 | HT report | FGB Minutes | Staff time |
|  | Tier 2 |  |  |  |  |  |
| 3.2.1 | Weekly teacher intervention time planned into curriculum | Teachers | Sept 20 | HT report | FGB minutes | 6 hours per week TA time Catch up funding (CUF) £3800 |
| 3.2.2 | Mentoring/Positive Play Continue with initiative and monitor. | HT SH | Sept 20 Dec 20 | HT report | FGB Minutes | DP funding |
| 3.2.3 | TA training Nov 20 (Catch Up® English and Maths ) | SH KT | Oct 20 | HT report | FGB minutes | CUF £800 |
| 3.2.4 | Identify areas for intervention -emotional and academic | All teachers | Oct 20 | HT report | FGB Minutes | Staff time |
| 3.2.5 | Final list of children needing Catch Up® | HT KS | 23 Oct 20 | HT report | FGB minutes | Staff time |
| 3.2.6 | Catch Up® Assessments to begin | HT KS | 2nd Nov 20 | HT report | FGB minutes | 8hrs of TA time (CUF 4 hours £2500) |
| 3.2.7 | Targeted learning packs for EHCP/GRIP. Development of recorded and live sessions for children entitled to 1:1 support in case of bubble closure. | Haven TAs HT | Oct 20 Feb 20 | HT report | FGB Minutes | Staff time |
| 3.2.8 | Pre- teaching Teacher identify children who would benefit from some pre-teaching. | All teachers | 6th Jan 20 |  |  | TA time- term 2 only 6 hours £1300 CUF |
| 3.2.9 | Training for TAs on pre-teaching | HT TAs | Jan 21 | HT report | FGB Minutes | Staff time |
| 3.2.10 | Pre-teaching sessions begin | All staff | Jan 21 | HT report | FGB Minutes | Staff time |
| 3.2.11 | Monitoring of pre-teaching | HT | Feb 21 | HT report | FGB Minutes | HT time |
| 3.2.12 | Parent teacher meetings to include SEND, DP and intervention information/discussion. | Teachers | Jan21 | HT report | FGB Minutes | Staff time School cloud £200 |
| 3.2.13 | Phonic training for TA | SEO NO’D AM | Dec 20 | HT report | FGB Minutes | Staff time |
| 3.2.14 | Phonic assessments | AM | Dec 20 | HT report | FGB Minutes | Staff time |
| 3.2.15 | Phonic interventions | AM | Jan 21 | HT report | FGB Minutes | Staff time |
|  | Tier 3 |  |  |  |  |  |
| 3.3.1 | Ensure every family has access to new system. (Hardware, passwords instruction issues rigorously pursued) Ensure vulnerable pupils are supported with access to Teams and other technologies. Identify other barriers (not tech) to learning at home for vulnerable families and engage with solutions. (Insight training) | HT RC | Nov 20 8th Dec 20 | HT report | FGB Minutes | Staff time |
|  | Christmas activities-singing. | HT | Dec 20 | HT report | FGB Minutes | Staff time |
| 3.3.2 | Sport and Music tuition | HT | March 21 | HT report | FGB minutes | Cost for non-DP student £500 CUF |
| 3.3.3 | Personal Growth. Continued (and adapted) use of Stars | All staff | March 21 | HT report | FGB Minutes | Staff time |